## Table of Contents
BIA Checklist'!A1
Table of Contents (click on hyperlink to each page / process)
Content | Description
BCP Structure | Recommended Content for a Business Continuity Plan (BCP)
1.1 Risk = Likelihood x Consequence | Step 1. Establish "areas of interest"/ "things you value" AND your “consequence thresholds".
1.2 BIA Worksheet | For each business function, assess the potential impact on both the things you value, and on the business as a whole should this function suffer an outage of varying durations due to a crisis.
1.3 BCP Worksheet | Use this framework to work through the identified RISK STATEMENTS for each critical function you are responsible for – one at a time. Develop and record your planning considerations by premising scenarios for the top three hazards/risks to which you may be exposed.
2 Translate to Action | Considerations regarding how to use the Risk Rating to prioritise and implement action plans.
3 Risk Register | Business Continuity Risk Register and Action Plan Overview.
Ref 1. RA Checklist | Risk Assessment Checklist
Ref 2. BIA Checklist | Business Impact Analysis Checklist
Ref 3. Glossary | The meanings of terms as used in this document
NB: The material in this workbook is provided for general information only and should not be relied upon for the purpose of a particular matter.

## BCP Structure
BIA Checklist'!A1
Recommended Content for a Business Continuity Plan (BCP)
Content | Description
Critical Business Functions | Details of the critical business functions, processes, critical assets, etc to which the BCP refers.
Triggers | Events, outage times, etc, that serve as triggers for the activation and deactivation of the BCP.
Processes | Processes, sub processes, etc that comprise the critical business function, or support the use of the asset/facility.
Responsibility | Name individual(s) with responsibility for the creation and maintenance of the plan.
Version Control and maintenance | Version number of the plan, date of creation, date of next review.
Critical success factors | What level of capability the critical business function, asset etc must achieve. Contractual and regulatory delivery requirements should also be specified.
Interdependcies | Key internal and external interdependcies.
Responsibilities | Responsibilities of named key managers and staff.
Contact Details | Business and after hours contact details of key managers, staff, suppliers customers and other stakeholders. Wherever possible each key role should also have a deputy identified and alternate suppliers listed.
Resources | Types and quantities of resources required to support the activation and implementation of the BCP. The plan should specify if dedicated resources are required or access to shared resources.
Outage Times | Where relevant identify maximum acceptable outage times and/or required recovery time for critical functions, processes, resources etc.
Workarounds & alternate solutions | Identify tasks that can still be undertaken following a disruption, those tasks that cannot be undertake and alternate solutions to those tasks to still achieve acceptable outcomes.
Continuity management tasks | Identify additional activities that have to be undertaken in response to the disruption (i.e. those activities beyond those associated with routine activities), for example assessment of the impacts of the disruption, co-ordination of asset reallocation, staff briefings to be held, etc.
Communication(s) | Summary of communication(s) requirements following activation of the plan.

## 1.1 Risk=LikelihoodxConsequence
Risk Assessment Criteria
Determining the Level of Risk
Step 1. Establish "areas of interest"/ "things you value" AND your “consequence thresholds".
Consequence Criteria
|  |  | 1 – Insignificant | 2 – Minor | 3 – Moderate | 4 – Major | 5 – Catastrophic
Likelihood | A - | The consequence is almost certain to occur in most circumstances | Medium (M) | High (H) | High (H) | Very High (VH) | Very High (VH)
| B - | The consequence is likely to occur frequently | Medium (M) | Medium (M) | High (H) | High (H) | Very High (VH)
| C - | Possible and likely for the consequence to occur at some time | Low (L) | Medium (M) | High (H) | High (H) | High (H)
| D - | The consequence is unlikely to occur but could happen | Low (L) | Low (L) | Medium (M) | Medium (M) | High (H)
| E - | The consequence may occur but only in exceptional circumstances | Low (L) | Low (L) | Medium (M) | Medium (M) | High (H)
Matrix* from page 55 of HB 436:2004 issued by Standards Australia to support the Australia / New Zealand Standard for Risk Management (AS/NZS 4360)
NB: The highest consequence tripped for ANY ONE "thing you value" sets THE OVERALL CONSEQUENCE (re the Risk Statement under consideration).
Consequence Criteria |  |  | Consequence Thresholds (Insert your agreed criteria against the things you value below)
Catastrophic |  |  | e.g. Descriptors of catastrophic consequences for 1. People; 2. Services; and 3. Reputation.
Major |  |  | e.g. Descriptors of major consequences for 1. People; 2. Services; and 3. Reputation.
Moderate |  |  | e.g. Descriptors of moderate consequences for 1. People; 2. Services; and 3. Reputation.
Minor |  |  | e.g. Descriptors of minor consequences for 1. People; 2. Services; and 3. Reputation.
Insignificant |  |  | e.g. Descriptors of insignificant consequences for 1. People; 2. Services; and 3. Reputation.

## 2 Translate to Action
Considerations regarding how to use the Risk Rating to prioritise and implement action plans.
Once the level of risk has been determined the following table may be of use in determining when to act to intervene and institute the control measures.
RISK LEVEL
Very High | Act immediately to mitigate the risk.Either eliminate, substitute or implement engineering control measures. | Remove the hazard at the source. An identified very high risk does not allow scope for the use of administrative controls , even in the short term.
High | Act immediately to mitigate the risk. Either eliminate, substitute or implement engineering control measures. | An achievable timeframe must be established to ensure that elimination, substitution or engineering controls are implemented.
| If these controls are not immediately accessible, set a timeframe for their implementation and establish interim risk reduction strategies for the period of the set timeframe. | NOTE: Risk (and not cost) must be the primary consideration in determining the timeframe.
Medium | Take reasonable steps to mitigate the risk. Until elimination, substitution or engineering controls can be implemented, institute administrative or personal protective equipment controls. These “lower level” controls must not be considered permanent solutions.The time for which they are established must be based on risk. At the end of the time, if the risk has not been addressed by elimination, substitution or engineering controls a further risk assessment must be undertaken. | Interim measures until permanent solutions can be implemented: • Develop administrative controls to limit the use or access. • Provide supervision and specific training related to the issue of concern. (See Administrative Controls below)
Low | Take reasonable steps to mitigate and monitor the risk. Institute permanent controls in the long term. Permanent controls may be administrative in nature if the hazard has low frequency, rare likelihood and insignificant consequence.
Hierarchy of Control Interventions identified may be a mixture of the hierarchy in order to provide as low as reasonably practicable exposure.
| Elimination | Eliminate the hazard.
| Substitution | Provide an alternative that is capable of performing the same task and is safer to use.
| Engineering Controls | Provide or construct a physical barrier or guard.
| Administrative Controls | Develop policies, procedures practices and guidelines, in consultation with employees, to mitigate the risk. Provide training, instruction and supervision about the hazard.
| Personal Protective Equipment | Personal equipment designed to protect the individual from the hazard.
The "Hierarchy of Control" can be useful - as can other heuristic devices such as "Prevention, Preparedness, Response & Recovery" or
"Engineering, Education, Encouragement, & Enforcement". As a general approach. A "mix of interventions" usually provides the best result.

## 3 Risk Register
Business Continuity Risk Register and Action Plan Overview
Reference - Issue No. : and/or Issue Date: | [5 empty] | Future Review date:
Identified Risks | Analysis & Evaluation |  |  | Existing controls described & evaluated |  |  | Further Actions
Risk Description List the EVENT and the EFFECT(s) in the form of Risk Statements(s) below. For example, "There is a risk that <INSERT EVENT> will <INSERT IMPACT> in/to/on/for/of <INSERT VULNERABLE ENTITY>. | Consequence (1, 2, 3, 4, or 5 - see Sheet 1) | Likelihood (A, B, C, D or E - see Sheet 1) | Risk level (L, M, H or VH - see Sheet 1) | What we do now to manage this risk. | Current Effectiveness | Accept Risk (Yes or No) | What we will do to reduce this risk | Assigned To | Future Risk Level Target (L, M, H or VH - see Sheet 1)
[6 empty] | No | Opportunities for improvement
Record by rows and cells as necessary.
|  | KEY | VH
H
M
L
Note on F7: Map the current approaches using a Matrix. Place Prevention, Preparedness, Response, Recovery down the left side; Place Education, Enforcement, Engineering Encouragement across the top.
Note on G7: (N = Not generally applied or only applied in isolated situations for example in less than 20% of cases; P = Partially applied, not usually documented or applied in less than 50% of cases; L = Largely applied, formally documented and largely repeatable or applied in up to 85% of cases; F = Fully applied, formally documented and fully repeatable or applied in more than 85% of cases.)
Note on I7: 1. Criteria used in evaluating the viability of any given option may include risk reduction potential; cost effectiveness and return on investment payback; continuity (sustainability) of effects; including leverage leading to further risk reducing actions by others; and compatibility (integration) with other actions that may be adopted; social issues, both in terms of participation in process and in terms of risk creation potential – especially risk imposition or transfer. 2. Use a Matrix to identify intervention options. Place Prevention, Preparedness, Response, Recovery down the left side; Place Education, Enforcement, Engineering Encouragement across the top. 3. For each plan or project -include a Work Breakdown Structure with outcome(s), output(s), milestone(s) & target date(s).

## Ref 1. RA Checklist
Risk Assessment Check List
Activity Status
Element | Issue | Not started | Delayed | On Target | Completed | Comments
Establishing the Context | Have the appropriate information resources been sourced?
Have the appropriate documents and other information sources been reviewed?
Has the scope of the risk assessment been determined and approved?
Have evaluation criteria been developed?
Have the disruption scenarios been developed?
Risk Identification and Analysis | Have sources of potential disruption risks been identified?
Have risks, their impacts and likelihoods been identified and assessed?
Risk Evaluation | Has the level of risk and the organisation’s tolerance to the each of the higher priority risks been determined?
Disruption Scenarios | Have disruption scenarios been developed from the identified risks?
Vulnerability analysis | Have organisational vulnerabilities to the risks/scenarios been identified?
| Total | 0 | 0 | 0 | 0

## Ref 2. BIA Checklist
The Business Impact Analysis Checklist
Activity Status
Element | Issue | Not started | Delayed | On Target | Completed | Comments
Critical Business Functions | Have the critical business functions been identified and confirmed by the 'owners' within the business?
Have the key processes and sub processes been identified?
Have key success factors been identified for each critical business function?
Have current (normal) resourcing requirements been identified?
Have disruption scenarios been developed?
Resources | Have resources required during a disruption been determined?
Dependencies and Interdependencies | Have dependcies for each critical business function been identified?
Have both internal and external interdependcies been considered?
Have both downstream and upstream interdependencies been identified?
Disruption Scenarios | Have disruption scenarios been modified and/or confirmed with 'owners' of critical business functions?
Disruption impacts | Have the impacts of disruption been determined for each critical business function?
Have a range of financial and non-financial impacts been assessed?
Have MAO Times and RTO been determined for each critical business functions?
Preparedness | Has current preparedness and capability been assessed?
Have treatments been developed to address preparedness and capability gaps?
Have alternate processes and workarounds been identified?
Are resources and skills available to implement workarounds?
| Total | 0 | 0 | 0 | 0

## Ref 3. Glossary
What is Risk?
From a business continuity perspective it is often convenient to view risk as any source disruption that may act as a barrier to the achievement of key business objectives. However, even apparently beneficial risks (the sudden collapse of a major competitor) can result in significant disruption (the sudden influx in new customers overwhelming capability and capacity to provide service).
Critical Business Functions -
From an understanding of the critical objectives it should be possible to identify critical business functions (groups of processes) that are required to achieve those objectives. The "acid test" to confirm a business function as "critical" is to determine to what extent the critical objectives will be achieved if a particular function is "removed". Although some functions may not appear to be critical in their own right, they may become regarded as critical because of the essential support they provide to other critical business functions.
Business Impact Analysis - Summary (BIA)
The Business Impact Analysis (BIA) provides an analysis of how key disruption risks could affect an organisations operations and what capabilities will be required to manage it. Specifically BIA provides the BC Manager / planner and the 'owners' of business functions with an agreed understanding of:
How they contribute to the achievement of the critical objectives
The key resources that are in place currently to achieve these critical objectives (eg people, processes, information and other infrastructure)
How the risks or disruption scenarios will impact on the capability of, and access to these key elements
The minium acceptable level of operation to achieve these objectives and nature of interdependencies and how they will be affected by the disruption
Maximum Acceptable (or Tolerable) Outage Times and Recovery Objectives
Maximum acceptable or tolerable outage (MAO or MTO) times should be determined for each of the critical business functions (down to process level where applicable), key IT applications and critical assets. The MAO time represents the maximum period of time that an organisation can tolerate the loss of capability of a critical business function, process, asset, or IT application. This should be determined by the 'owners' of the critical business function.
Recovery Time Objective (RTO)
A RTO represents the required level of capability that the organisation aims to recover within a defined time frame.
Alternate Workarounds
There will be circumstances when the available capability is not sufficient to maintain processes and critical business functions, or the delay before recovery occurs is not acceptable. At such times the only means available to continue the achievement of critical objectives is to implement alternate workarounds. The commonest approach to alternate workarounds is the use of manual processes to replace the non available automated processes. For example, an effective alternate workaround for the loss of a word processing application may be the implementation of pen and paper for document preparation.
Criteria to consider in identifying and evaluating workarounds include the degree to which:
The alternate process can be conducted in the absence of technology or specialised equipment in the event it is not accessible;
The alternate process can be practically implemented following a disruption
The alternate process will produce outputs that a meet a minium acceptable standard;
Significant OHS issues arising as a result of the adoption of the alternate process can be effectively managed;
Sufficient knowledge and skills can be accessed to manage and operate the alternate process; and
The alternate process will comply with any governance, regulatory or contractual requirements.
Resource Requirements
Once the normal day-to-day resource requirements have been determined, it is necessary to challenge staff on which of each of these resources is absolutely essential to achieve the required level of operation to meet the critical business objectives in the event of a disruption. The aim here is to identify the minimum resorcin that must be made available following a disruption. The primary outcome of this step should produce two lists for each critical business function: 'normal resource requirements' and 'disrupted resource requirements'
Disruption scenarios
The risk assessment can produce a large number of specific disruption risks. Trying to use this volume of information as the basis for the BIA and for subsequent planning can be a daunting and unnecessary task.
There is there a need to consider developing the outputs for the risk assessment to both simplify the conduct of the BIA and to improve the flexibility and relevance of its outputs. It can often be more effective to group risks into broader risk scenario's (or 'meta' risks) on which to base the BIA and any subsequent development of plans.
Response Strategies
The development of response strategies is concerned with determining how an organisation will respond to an incident, and the manner in which the different elements of this overall response will interact
The recovery and restoration response aimed at returning the organisation to a long term operationally acceptable and sustainable capability. In developing a recovery and restoration response strategy it will be necessary to consider what can be practically identified and planned for and what will be decided on during the actual response.